## Slide 1
Project Setup
Matthew
Checkstyle
Matthew
HyPeerWebDatabase
Konrad
HyPeerWeb
Brian, Huy
Node
Trevor
Maintainence
Phase 1: Database
Phase 2: Add
Connections
Huy, Matthew
Validate Given Tests
Matthew
Recurring; Project deadlines
JavaDoc & Junit
Connections: Trevor
Node: Brian, Huy
HyPeerWeb: Matthew
HyPeerWebDatabase: Konrad

## Slide 2
Find Deletion Point
Huy
Start: 10/8/2012
End: 10/15/2012
Actual: 10/12/2012
Update Connections
Trevor, Konrad
Start: 10/8/2012
End: 10/15/2012
Actual: 10/13/2012
Review and Testing
Brian, Matthew
Start: 10/15/2012
End: 10/16/2012
Actual: 10/16/2012
Phase Three

## Slide 3
Database Tests
Trevor
Start: 10/17
Planned: 10/30
Actual: 10/23
HyPeerWeb Tests
Matthew
Start: 10/17
Planned: 10/30
Actual: 10/30
Visitor Tests
Konrad
Start: 10/17
Planned: 10/30
Actual: 10/30
Node Tests 1
Huy
Start: 10/17
Planned: 10/30
Actual: 10/30
Node Tests 2
Brian
Start: 10/17
Planned: 10/30
Actual: 10/29
Setup Visitor Pattern
Matthew
Start: 10/17
Planned: 10/30
Actual: 10/27
Finish Visitor Pattern
Konrad
Start: 10/17
Planned: 10/30
Actual: 10/27
Review
Brian, Matthew
Start: 10/17
Planned: 10/30
Actual: 10/30
Phase Four
Note: MM/DD